## Sheet1
|  | Design & Analysis |  |  | First steps & Connecting |  |  | H/M priority features |  |  | Database & Implementation |  |  | Finishing
| Sprints | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5
| Weeks | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Project plan + prototype + URS | bar: Sprint 1 2
Database design + UML + Test report | bar: Sprint 1 3
Activities | First research ( Security ) | bar: Sprint 1 4
First steps of implementation | bar: Sprint 2 5
Second research ( React & API ) | bar: Sprint 2 6
Basic CRUD functionality | bar: Sprint 2 6 to Sprint 2 7
High priority features | bar: Sprint 3 8 to Sprint 3 9
Medium priority features | bar: Sprint 3 10
Storing the data in a database | bar: Sprint 4 11
Implementing unfinished features | bar: Sprint 4 12 to Sprint 4 13
Finishing the project | bar: Sprint 5 14 to Sprint 5 16